MATCH EXPLAINER

Development Plan, Test Plan and Agent Brief

Phases, tasks, tests, demo script, Git workflow and ready-to-paste prompts for Claude Code and Codex

| Field | Value |
| --- | --- |
| Document ID | MX-04 |
| Project | Match Explainer (working title) |
| Version | 1.0 (baseline) |
| Date | 25 October 2026 |
| Status | Draft for feasibility review |
| Audience | Project owner, evaluators, AI coding agents (Claude Code / Codex) |

Contents

1. Delivery approach and gates

2. Phase plan and timeline

3. Work breakdown (tasks)

4. Definition of done

5. Test plan and test cases

6. Demo script and viva preparation

7. Git workflow and connecting your repository

8. Agent instruction files (CLAUDE.md and AGENTS.md)

9. Prompt A: feasibility and feedback review

10. Prompt B: build prompts by phase

11. Owner checklist and open decisions

# 1. Delivery approach and gates

Work proceeds as a vertical slice first: get one goal moment from raw data to an animated replay on screen early, then widen. Four gates control quality and scope.

| Gate | When | Exit condition |
| --- | --- | --- |
| G1 Data verified | End of Phase 0 | IDs, files and 360 availability asserted by verify_ids.py; skeleton repo pushed |
| G2 Pipeline complete and scope freeze | End of Phase 4 | All pipeline outputs for the demo match validate against schemas; xG metrics file exists. No new features after this gate; only the cut list may shrink. |
| G3 Feature complete | End of Phase 7 | All M requirements work in the browser, offline |
| G4 Demo ready | End of Phase 8 | Tests green, README done, backup recording made, rehearsal done |

# 2. Phase plan and timeline

| Phase | Name | Hours | Cumulative | Outputs |
| --- | --- | --- | --- | --- |
| P0 | Setup and data verification | 1.0 | 1.0 | Repo skeleton, data cloned, verify_ids.py, config files |
| P1 | Loader, normaliser, match metrics | 1.5 | 2.5 | summary.json (stats), coordinate tests |
| P2 | Positions, lines, shape | 1.0 | 3.5 | positions.json |
| P3 | Key moments and build-up, 360 snapshots | 1.0 | 4.5 | moments.json (without text) |
| P4 | xG features, training, evaluation, prediction | 1.5 | 6.0 | Model, metrics, calibration plot, shots.json G2 |
| P5 | Explanation layer and templates | 1.0 | 7.0 | Text in moments.json and summary.json |
| P6 | Web shell, summary, pitch view, shots | 2.0 | 9.0 | Working site without replay |
| P7 | Replay engine, snapshots, model card, glossary | 1.5 | 10.5 | Animated moments G3 |
| P8 | Testing, polish, docs, demo rehearsal | 1.5 | 12.0 | Release G4 |

Parallel work: P4 (model training) can run in the background while P5 and P6 are built, which brings calendar time down to roughly 9 to 10 hours. If the deadline leaves fewer than 8 hours: build P0 to P3, a simplified P4 (logistic regression only), template text only, and P6 to P7 without the pass network, momentum graph or match picker.

# 3. Work breakdown (tasks)

| ID | Ph | Task | Depends | Done when |
| --- | --- | --- | --- | --- |
| T-01 | P0 | Create repo skeleton, .gitignore, requirements.txt, Makefile, README stub | - | Folders exist; first commit pushed |
| T-02 | P0 | Clone StatsBomb open data (shallow) to data/raw/open-data | - | competitions.json readable |
| T-03 | P0 | Write scripts/verify_ids.py (competition 43, season 106, match 3869685, events, lineups, 360 present) | T-02 | Script prints OK or precise errors |
| T-04 | P0 | Write config/default.json and train_competitions.json; choose training competitions that exist on disk | T-02 | Config loads |
| T-05 | P1 | load.py: read and validate competitions, matches, lineups, events, 360 | T-03 | FR-D1, FR-D2 tests pass |
| T-06 | P1 | normalize.py: flatten, time columns, exclude period 5, coordinate mirror helper | T-05 | FR-D3, FR-D4 tests pass |
| T-07 | P1 | metrics.py: possession, passes, shots, cards, fouls, corners | T-06 | Totals equal independent recomputation |
| T-08 | P1 | JSON Schema files in schemas/ and validate.py schema check | T-06 | Sample outputs validate |
| T-09 | P2 | positions.py: windows, average positions, role groups | T-06 | Positions plausible when plotted |
| T-10 | P2 | Lines, shape metrics, block labels, k-means cross-check | T-09 | Labels differ across windows |
| T-11 | P3 | moments.py: candidate detection, scoring, spacing, cap | T-06 | Six goal moments for demo match |
| T-12 | P3 | Build-up extraction and step conversion | T-11 | Sequence ends at shot; same possession |
| T-13 | P3 | 360 snapshot join and offside line | T-11 | Snapshots present for goal moments |
| T-14 | P4 | xg_features.py with leakage guard test | T-06 | No forbidden feature |
| T-15 | P4 | xg_train.py: baselines, models, group split, metrics, calibration plot | T-14 | xg_metrics.json written |
| T-16 | P4 | xg_predict.py: demo-match shots, penalties, team totals | T-15 | shots.json valid |
| T-17 | P4 | Attach xG to moments and summary; run schema validation (G2) | T-16 | All outputs valid |
| T-18 | P5 | Templates and rule-based "why" lines | T-17 | Text for every moment with --no-llm |
| T-19 | P5 | LLM call, prompt files, validator, cache, retry, fallback | T-18 | Forced failure returns template |
| T-20 | P5 | Match story and team summaries | T-19 | Present and labelled |
| T-21 | P6 | Web shell: nav, router, loader, state, style tokens, footer attribution | T-17 | Pages switch; data loads |
| T-22 | P6 | Summary page with stat cards and tooltips | T-21 | FR-M tests pass |
| T-23 | P6 | SVG pitch factory, positions, lines, slider, shape metrics | T-21 | FR-P tests pass |
| T-24 | P6 | Shot map and momentum graph | T-21 | Hover shows xG and player |
| T-25 | P7 | Replay engine: timeline, arrows, ball, controls, reduced motion | T-21 | FR-A1 to A3, A6 pass |
| T-26 | P7 | Snapshots and offside line overlay | T-25 | FR-A4, A5 pass |
| T-27 | P7 | Moments page integration and filter | T-25 | List and replay linked |
| T-28 | P7 | Model card and glossary pages | T-15 | FR-X7, FR-G1 pass |
| T-29 | P7 | Optional: pass network, match picker, highlight links | T-21 | FR-N1, S2, L1 pass |
| T-30 | P8 | Run full test suite; fix defects | all | All tests green |
| T-31 | P8 | Accessibility and offline checks (checklist) | T-27 | NFR-2, NFR-4 pass |
| T-32 | P8 | README, model card text, screenshots, attribution check | T-28 | Reviewer can run in under ten commands |
| T-33 | P8 | Record 3-minute backup video; export PDF screenshots; rehearse demo twice | T-30 | Backups stored outside repo and on a phone or pen drive |

# 4. Definition of done

- Code merged to main with passing tests and linting (ruff or flake8 if installed).

- Requirement acceptance criteria in MX-02 verified.

- Outputs validate against JSON Schemas.

- No secrets, raw data or large files committed.

- Documentation updated if behaviour changed (README, MX-03 if design changed).

- Commit message follows the convention in Section 7.

# 5. Test plan and test cases

## 5.1 Strategy

| Level | Tools | Scope |
| --- | --- | --- |
| Unit | pytest | Normaliser, formulas, feature engineering, validators, moment detection |
| Data validation | pytest with JSON Schema | Every output file; counts versus the matches file |
| Model evaluation | Script and metrics file | Leakage guard, baselines, calibration, benchmark comparison |
| Integration | pytest, run_pipeline on a fixture | End-to-end on a small fixture and on the demo match |
| UI manual | Checklist in browser, keyboard only run, offline run | All screens, controls, tooltips |
| Demo rehearsal | Stopwatch, two full run-throughs | Timing and recovery from a failure |

## 5.2 Test cases

| TC | Req | Test | Expected |
| --- | --- | --- | --- |
| TC-01 | FR-D1 | Run pipeline with network disabled | Completes |
| TC-02 | FR-D2 | Remove the events file for the match | Error names match_id and file |
| TC-03 | FR-D3 | mirror(mirror(p)) equals p for random points | True |
| TC-04 | FR-D3 | All goal events of the demo match, after orientation, have shot start x at least 80 | True |
| TC-05 | FR-D4 | Remove period 5 events and recompute possession and positions | Values unchanged |
| TC-06 | FR-M1 | Score in summary equals matches file (3-3) and shootout reported separately | Equal |
| TC-07 | FR-M2 | Recompute shots, passes and cards independently | Equal to summary |
| TC-08 | FR-M2, M4 | Possession home + away equals 100 percent; method string present | True |
| TC-09 | FR-M3 | Every stat label has non-empty tooltip text | True |
| TC-10 | FR-P1 | Pitch SVG viewBox is 120 x 80 | True |
| TC-11 | FR-P2 | Changing window changes player positions | Different values |
| TC-12 | FR-P3 | DEF line x is less than MID x which is less than ATT x for each team in the full-match window | True |
| TC-13 | FR-P4, P5 | Slider reaches 120 minutes; at least two different block labels across windows | True |
| TC-14 | FR-K1 | Goal moments for the demo match | Exactly 6 |
| TC-15 | FR-K2 | Moment count at most cap; pairwise gaps at least min_gap_s (goals exempt) | True |
| TC-16 | FR-K3 | moments.json validates against schema | Valid |
| TC-17 | FR-K4 | Each sequence: same possession id, last step is the shot, length at most 12 | True |
| TC-18 | FR-A1 | Open each moment and press play | Arrows drawn, ball moves |
| TC-19 | FR-A2 | Pause, resume, restart, 0.5x, scrub with keyboard | All work |
| TC-20 | FR-A3 | Step labels visible and key pass highlighted | Visible |
| TC-21 | FR-A4, A5 | Snapshot overlay for goal moments; offside line equals max defender x | True |
| TC-22 | FR-A6 | Enable reduced motion in the OS or browser | Static steps shown |
| TC-23 | FR-X1 | Training set excludes penalties, own goals, period 5, and the demo competition | Counts logged and correct |
| TC-24 | FR-X2 | Feature list contains none of the forbidden names | Test passes |
| TC-25 | FR-X3 | Metrics include baseline and both models | Present |
| TC-26 | FR-X4 | Metrics file has log loss, Brier, AUC, calibration, StatsBomb comparison; PNG exists | Present |
| TC-27 | FR-X4 | Full model log loss is lower than distance-angle baseline on test set | True (else report honestly and investigate) |
| TC-28 | FR-X5 | All predicted xG are in [0, 1]; penalties equal the stored rate; team totals equal sum of shots | True |
| TC-29 | FR-E1 | Every moment has text and why | True |
| TC-30 | FR-E2 | Run the site with no API key and no internet | Text shown |
| TC-31 | FR-E3 | Force LLM error | Template text used, source = template |
| TC-32 | FR-E4, E5 | Inject a fake player name into LLM output; check label presence | Rejected; label visible |
| TC-33 | FR-N1 | Pass network renders for both teams with at least one edge | True |
| TC-34 | FR-N2 | Momentum graph spans minutes 0 to the end of extra time | True |
| TC-35 | FR-G1, L1 | Glossary has at least 15 terms; highlight link opens a new tab and nothing is embedded | True |
| TC-36 | FR-C1 | Footer attribution on every page | Present |
| TC-37 | NFR-1 | Measure load time and frame rate on the demo laptop | At most 3 s; at least 30 fps |
| TC-38 | NFR-2 | Turn off Wi-Fi; use every screen | No failures |
| TC-39 | NFR-3 | Three non-football users each explain one moment | 3 of 3 succeed |
| TC-40 | NFR-4 | Keyboard-only run; contrast check of text and controls | Pass |
| TC-41 | NFR-7 | make all on a clean clone with the data present | Identical numeric outputs |
| TC-42 | NFR-8, 9 | Scan repo for keys; check licence and attribution text | No secrets; text present |

Known sanity oracle for the demo match: six goals (Argentina at about 23 and 36 minutes and 108; France at about 80, 81 and 118; verify exact minutes against the data). Use these as eyeball checks, but let the data decide.

# 6. Demo script and viva preparation

## 6.1 Five-minute demo script

| Time | Action | Say |
| --- | --- | --- |
| 0:00 | Open home page | "Commentary tells you what happened. This tells you why, in plain words." |
| 0:30 | Hover xG and possession | "Every term explains itself; xG means the quality of a chance." |
| 1:00 | Pitch view, drag the slider through the first half and extra time | "These lines show how high each team defended in each phase." |
| 2:00 | Open an 80th-minute goal moment, press play | "The data rebuilds the move; the text explains why it worked." |
| 3:00 | Show the snapshot and offside line | "This is the 360 data: only the players visible on camera." |
| 3:30 | Open Model card | "xG is trained on tens of thousands of shots, split by competition to avoid leakage; here is the calibration and comparison with StatsBomb." |
| 4:30 | Show repo and README | "Everything rebuilds with one command, and the same pitch code can later power the video version." |

## 6.2 Likely questions and answers

| Question | Answer outline |
| --- | --- |
| What is the ML here? | A supervised xG classifier trained on historical shots; logistic regression baseline and gradient boosting; evaluated by log loss, AUC and calibration. |
| Why not predict the winner? | Outcome prediction is noisy and not explanatory; xG explains chance quality, which is what the app teaches. |
| How did you avoid leakage? | Only pre-shot features, forbidden-feature test, competition-level split, StatsBomb xG used only as a benchmark. |
| Why not just use StatsBomb xG? | It is shown for comparison. Training our own demonstrates the method, and the metrics show the honest gap. |
| How accurate are the tactics labels? | They are rule-based on average positions from event data, so they are approximate; thresholds are configurable and the UI says so. |
| Is the LLM reliable? | It only sees structured facts, output is validated, text is cached, templates are the fallback, and everything is labelled automated analysis. |
| How is this different from existing tools? | Existing tools target analysts; this targets beginners with animated, plain-language explanations and a transparent method. |
| What are the limits? | Event data has no continuous tracking; 360 shows visible players only; one competition for demo; positions are averages. |
| What would you do next? | Add more matches, then a computer-vision pipeline for video using the same pitch and replay components. |
| Is it legal to use the data? | Free with attribution under StatsBomb's terms; no broadcast footage is hosted. |

# 7. Git workflow and connecting your repository

## 7.1 Create and connect the repository

No repository is connected yet. Use one of the two routes below from the project folder. Replace <user> with your GitHub username.

# Route A: GitHub CLI (recommended)

git init -b main

git add .

git commit -m "chore: initial docs and project skeleton"

gh auth login                                   # once

gh repo create match-explainer --public --source=. --remote=origin --push

# Route B: create an empty repo on github.com first, then

git init -b main

git remote add origin https://github.com/<user>/match-explainer.git

git add . && git commit -m "chore: initial docs and project skeleton"

git push -u origin main

## 7.2 Using Claude Code or Codex with the repository

- Place the four .docx files in docs/ and commit them. Also export them to Markdown (pandoc MX-03_*.docx -o docs/MX-03.md) so agents read them reliably.

- Add CLAUDE.md (for Claude Code) and AGENTS.md (for Codex) at the repository root using Section 8.

- Open the terminal in the repository folder and start the agent (claude for Claude Code; Codex CLI or the Codex web app connected to the GitHub repo).

- Paste Prompt A first (feasibility and feedback). Read the answer, update the documents if needed, then paste Prompt B phase by phase.

- Review each pull request or diff yourself before merging; run pytest and the site locally.

## 7.3 Branching and commits

- main is always runnable. Work on feat/<task-id>-<short-name> branches and merge by pull request (or squash locally for speed).

- Commit format: type(scope): summary, for example feat(moments): detect goals and red cards (T-11). Types: feat, fix, docs, test, chore, refactor.

- Tag gates: g1-data-verified, g2-pipeline-complete, g3-feature-complete, g4-demo-ready.

- Commit the processed demo bundle, the trained model and the LLM cache so the repo runs without raw data or keys.

## 7.4 .gitignore essentials

data/raw/

data/interim/*

!data/interim/llm_cache.json

.venv/

__pycache__/

.env

*.log

node_modules/

.DS_Store

# 8. Agent instruction files (CLAUDE.md and AGENTS.md)

Create both files with identical content so either agent follows the same rules.

# Match Explainer - agent instructions

## What this is

Static website + offline Python pipeline that explains a finished football match to

beginners using StatsBomb open data. Specs live in docs/ (MX-01 to MX-04). Follow MX-02

requirement IDs and MX-03 design. Do not add features outside the MX-02 M and S lists.

## Commands

- Setup: python -m venv .venv && pip install -r requirements.txt

- Verify data: python scripts/verify_ids.py

- Train xG: python -m pipeline.xg_train

- Build match: python -m pipeline.run_pipeline --match-id 3869685 [--no-llm]

- Test: pytest -q

- Serve site: python -m http.server -d web 8000

## Rules

- Read raw StatsBomb JSON directly; do not call external data APIs at runtime.

- Never use shot.outcome, shot.end_location or shot.statsbomb_xg as xG features.

- Exclude period 5 (shootout) from possession, positions and xG training.

- Keep coordinates in the 120 x 80 StatsBomb frame; mirror the away team only at export.

- LLM text must come from structured facts, be validated, cached, and fall back to templates.

- Web app: vanilla JS + SVG, no framework, no third-party runtime requests, works offline.

- Keep modules small (about 300 lines), add type hints and tests for each module.

- Do not commit secrets, raw data or large files. API key only via ANTHROPIC_API_KEY.

- Always keep the StatsBomb attribution footer and the "Automated analysis" labels.

- If a spec detail conflicts with the real data (IDs, field names), stop and report it

rather than guessing; propose the doc fix.

## Workflow

- One task (T-xx) per branch and commit. Run pytest before committing.

- Update docs if behaviour changes. Tag gates G1 to G4 as defined in MX-04.

# 9. Prompt A: feasibility and feedback review

Paste this into Claude Code or Codex after the documents are in the repository (or attach the four documents). It asks for a critical review, not an implementation.

You are a senior engineer and data scientist reviewing a project plan before any code is written.

Read docs/MX-01 to MX-04 fully. Do NOT write application code yet.

Review goals:

1. Feasibility: is the MVP achievable in about 12 focused hours with an AI coding agent?

Give a verdict (go / go with cuts / no-go) and the reasoning.

2. Correctness of data assumptions. If you have network access, verify against the

statsbomb/open-data repository: competition_id 43 / season_id 106 for FIFA World Cup 2022,

match_id 3869685 for the final, existence of data/three-sixty/3869685.json, event field

names used in MX-02 and MX-03, coordinate orientation and mirroring, period numbering,

penalty and own-goal representation, card fields, and the licence/attribution terms.

List every mismatch.

3. Technical design: weaknesses in the xG plan (leakage, split, features, evaluation),

the lines/shape algorithms, the moment detection and the replay model. Suggest concrete fixes.

4. Scope and schedule: check requirement priorities, task estimates and dependencies. Propose a

minimum viable cut that still shows a trained model and animated moments, in case only 8 hours remain.

5. Risks missing from the register, and test gaps.

6. Documentation quality: contradictions, ambiguities, missing details an implementer would need.

Output format:

- Verdict and top 5 risks (one line each).

- A table: finding | document and section | severity (high/med/low) | recommended change.

- Verified facts versus unverified assumptions.

- A prioritised list of edits to the documents (do not apply them until I approve).

- Questions you need answered before building.

# 10. Prompt B: build prompts by phase

Use one prompt per phase. Each tells the agent to stay inside the specification and to stop at the gate. Replace the bracketed task range as you go.

Context: follow docs/MX-01 to MX-04 and CLAUDE.md. Work only on tasks [T-05 to T-08] (Phase P1).

For each task: implement, add pytest tests listed in MX-04 section 5.2 for the covered

requirements, run the tests, then commit with the message format in MX-04 section 7.3.

Rules: no features outside MX-02 M and S lists; if real data contradicts the docs, stop and report.

When the phase is finished, print: tasks completed, tests run and result, deviations from the docs,

and what you need from me. Stop at the gate; do not start the next phase.

| Phase | Tasks | Extra instruction for the prompt |
| --- | --- | --- |
| P0 | T-01 to T-04 | Create the skeleton and verify IDs; print a verification report before continuing |
| P1 | T-05 to T-08 | Show me possession and shot totals next to the matches file score |
| P2 | T-09 to T-10 | Save a matplotlib check image of average positions and lines for three windows |
| P3 | T-11 to T-13 | Print the detected moments table (minute, player, type, xG) for review |
| P4 | T-14 to T-17 | Train in the background; show metrics, leakage test result and the calibration plot |
| P5 | T-18 to T-20 | Run with --no-llm first, then with the LLM; show validator rejections |
| P6 | T-21 to T-24 | Start the dev server and describe each screen; list any console errors |
| P7 | T-25 to T-29 | Test with keyboard only and with reduced motion; confirm offline behaviour |
| P8 | T-30 to T-33 | Run the full test plan; produce a defect list and a final checklist against MX-02 acceptance criteria |

# 11. Owner checklist and open decisions

## 11.1 Things only you can do

- Create the GitHub repository and connect it (Section 7.1).

- Run the data clone if the agent environment cannot reach GitHub.

- Provide an LLM API key (optional) as an environment variable.

- Confirm with your teacher whether a trained model is required (this design includes one) and what the submission format is.

- Test with three non-football users; rehearse the demo twice; keep a backup video.

## 11.2 Open decisions

| # | Decision | Default if undecided |
| --- | --- | --- |
| D1 | Use an LLM API for explanations? | Yes if a key exists, otherwise templates only |
| D2 | Which training competitions? | Whatever subset downloads quickly: a few league seasons, World Cup 2018, Euro 2020 |
| D3 | Include match picker and extra matches? | No for MVP; add after G3 |
| D4 | Public hosting on GitHub Pages? | Yes after reading StatsBomb licence |
| D5 | Which highlights URL for external links? | Official channel link supplied by you; field stays empty until then |

Honesty note for submission: the app explains matches from event data; tactical labels are approximate; xG accuracy is reported with its limits; generated text is labelled. Stating this openly makes the project stronger, not weaker.